## Plan
International hiring plan template
One row per planned hire. Fill the yellow cells. The grey cells are formulas. Delete the example row before use.
# | Role | Team and hiring manager | Country | Route | Target start date | Lead time from signed offer to start (weeks) | Latest date to sign the offer | Monthly employer cost, local currency | Cost currency | Exchange rate to your currency (1 local = ?) | Monthly employer cost, your currency | Where the cost figure came from, and its date | Status | Blockers and notes
1 | Backend engineer (example, delete) | Platform, Dana | Country A | Employer of record | 2027-02-01 | 10 | 2026-11-23 | 6000 | EUR | 0.86 | 5160 | Employer cost calculator, read on the date shown here | Idea | Example row only. Replace every value, including the lead time.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
[10 empty] | Total monthly cost, hires not on hold or cancelled | 5160
Legend: yellow cells are for you to fill in; grey cells are formulas. Blue italic text is the example row: delete it. Exchange rate: enter units of your currency per 1 unit of local currency, and note the source and date in column M.
Formulas:
Latest date to sign the offer = IF(OR([Target start date]="",G5=""),"",[Target start date]-G5*7)

## Country checks
Country checks
One row per country on the Plan tab. Take each answer from the country guide or the official authority, and write the date you read it.
Country | Route chosen | Who can employ the person there, and what they need to start | Right-to-work and visa steps, and how long they take | Probation and notice terms (from the guide) | Benefits people expect there | Tax and social security registrations needed | Link to the country guide | Date checked | Owner

## How to use
How to use this template
1. List every hire you expect in the next 12 months on the Plan tab, one row each, even if the role is only an idea.
2. Choose the route for each: contractor, employer of record, or your own entity. Write down why, in the notes column.
3. Enter the target start date and the lead time in weeks. The sheet works out the latest date to sign the offer. Take the lead time from your provider and the country guide, and include any visa, permit or registration step.
4. Cost each hire. Use an employer cost calculator or a written quote, enter the monthly employer cost in local currency, the rate to your currency and where the figure came from.
5. Fill the Country checks tab once for each country, from the country guide.
6. Review the plan each month. Change the status, move dates and update costs.
What it does not do
It does not decide the route for you, and it does not hold any country's rules. It is a planning sheet.
Source
Teamed international hiring plan template, version 1.0, 20 October 2026. Free to copy and change. Published at https://www.teamed.global/resources/international-hiring-plan-template